## Sheet1
David Raymond Christofer
Category | Test Case | Precondition | Step | Expected Result | Actual Result | Status
Authentication Register | Register with null email null password null fullname | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/auth/register 3. Input email : " ", Input password : " ", Input fullname : " " 4. Klik tombol send | 400, Bad Request Muncul pesan error email is required | 400, Bad Request Muncul pesan error email is required | PASSED
| Register with valid email null password null fullname | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/auth/register 3. Input email : " someone@mail.com", Input password : " ", Input fullname : " " 4. Klik tombol send | 400, Bad Request Muncul pesan error password is required | 400, Bad Request Muncul pesan error password is required | PASSED
| Register with null email valid password null fullname | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/auth/register 3. Input email : " ", Input password : " 123123", Input fullname : " " 4. Klik tombol send | 400, Bad Request Muncul pesan error email is required | 400, Bad Request Muncul pesan error email is required | PASSED
| Register with null email null password valid fullname | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/auth/register 3. Input email : " ", Input password : " ", Input fullname : "Firstname Lastname " 4. Klik tombol send | 400, Bad Request Muncul pesan error email is required | 400, Bad Request Muncul pesan error email is required
| Register with valid email valid password null fullname | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/auth/register 3. Input email : "someone@mail.com ", Input password : " 123123", Input fullname : " " 4. Klik tombol send | 400, Bad Request Muncul pesan error fullname is required | 400, Bad Request Muncul pesan error fullname is required | PASSED
| Register with valid email null password valid fullname | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/auth/register 3. Input email : "someone@mail.com ", Input password : " ", Input fullname : " Fullname Lastname" 4. Klik tombol send | 400, Bad Request Muncul pesan error password is required | 400, Bad Request Muncul pesan error password is required | PASSED
| Register with null email valid password valid fullname | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/auth/register 3. Input email : " ", Input password : " 123123", Input fullname : " Fullname Lastname" 4. Klik tombol send | 400, Bad Request Muncul pesan error email is required | 400, Bad Request Muncul pesan error email is required | PASSED
| Register with valid email valid password valid fullname | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/auth/register 3. Input email : " someone@mail.com", Input password : " 123123", Input fullname : " Fullname Lastname" 4. Klik tombol send | 200 Ok | 400, Bad Request | PASSED
Authentication Login | Login with url and body | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/auth/login 3. Input email : " someone@mail.com", Input password : " 123123", 4. Klik tombol send | 200 Ok Akan muncul data yang ada | 200 Ok Akan muncul data yang ada | PASSED
| Login with url and invalid body | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/auth/login 3. Input email : " siboro@gmail.com", Input password : " 123123", 4. Klik tombol send | 400 Akan muncul error | 400 Akan muncul error | PASSED
| Login with url and valid body wrong password | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/auth/login 3. Input email : " someone@mail.com", Input password : " 000999", 4. Klik tombol send | 400 Akan muncul error | 400 Akan muncul error | PASSED
Authentication Get User Information | Get user information with valid url | 1. Menyiapkan URL | 1. Method GET 2. URL : https://alta-shop.herokuapp.com/api/auth/info 3. Klik tombol send | 401 Akan muncul error | 401 Akan muncul error | PASSED
Hello Index | Get user index hello | 1. Menyiapkan URL | 1. Method GET 2. URL : https://alta-shop.herokuapp.com/api/auth/hello 3. Klik tombol send | 200 Akan muncul data | 200 Akan muncul data | PASSED
Order Create a new order | Create new order with valid token | 1. Menyiapkan URL 2. Menyiapkan token | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/orders 3. Input body 4. Klik tombol send | 400 Akan muncul error | 400 Akan muncul error | PASSED
Order Get all order | Get all order with valid token | 1. Menyiapkan URL 2. Menyiapkan token | 1. Method GET 2. URL : https://alta-shop.herokuapp.com/api/orders 3. Klik tombol send | 401 Akan muncul error message | 401 Akan muncul error message | PASSED
Order Get order by id | Get order by id | 1. Menyiapkan URL | 1. Method GET 2. URL : https://alta-shop.herokuapp.com/api/orders 3. Klik tombol send | 401 Akan muncul error message | 401 Akan muncul error message | PASSED
Products Get all products | Get all product | 1. Menyiapkan URL | 1. Method GET 2. URL : https://alta-shop.herokuapp.com/api/products 3. Klik tombol send | 200 Ok akan muncul data data | 200 Ok akan muncul data data | PASSED
Products Create a new product | Create a new product with valid body | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/products 3. Input name : "Sony PS 5" 4. Input description : "play has no limits" 5. Input price : "299" 6. Input ratings : "4" 7. Klik tombol send | 200 Ok akan membuat data baru | 200 Ok akan membuat data baru | PASSED
| Create a new product with invalid body | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/products 3. Input name : "" 4. Input description : "" 5. Input price : "" 6. Input ratings : "" 7. Klik tombol send | 500 akan muncul error message | 500 akan muncul error message | PASSED
Products Get product by id | Get product with valid id | 1. Menyiapkan URL | 1. Method GET 2. URL : https://alta-shop.herokuapp.com/api/products/25 3. Klik tombol send | 200 Ok Akan menampilkan id yang dituju | 200 Ok Akan menampilkan id yang dituju | PASSED
| Get product with invalid id | 1. Menyiapkan URL | 1. Method GET 2. URL : https://alta-shop.herokuapp.com/api/products/00 3. Klik tombol send | 404 not found Akan muncul record not found | 404 not found Akan muncul record not found | PASSED
Products Delete a product | Delete product with valid id | 1. Menyiapkan URL | 1. Method DELETE 2. URL : https://alta-shop.herokuapp.com/api/products/25 3. Klik tombol send | 200 Ok Data akan terhapus | 200 Ok Data akan terhapus | PASSED
| Delete product with invalid id | 1. Menyiapkan URL | 1. Method DELETE 2. URL : https://alta-shop.herokuapp.com/api/products/00 3. Klik tombol send | 500 Akan muncul error message | 500 Akan muncul error message | PASSED
Products Assign a product rating | Assign a product rating with valid url | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/products/16/ratings 3. Input ratings : 4 4. Klik tombol send | 401 | 401 | PASSED
| Assign a product rating with invalid url | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/products/00/ratings 3. Input ratings : 4 4. Klik tombol send | 401 | 401 | PASSED
Products Get product rating | Get product rating with valid url | 1. Menyiapkan URL | 1. Method GET 2. URL : https://alta-shop.herokuapp.com/api/products/17/ratings 3. Klik tombol send | 200 Ok akan muncul rating yang dituju | 200 Ok akan muncul rating yang dituju | PASSED
| Get product rating with invalid url | 1. Menyiapkan URL | 1. Method GET 2. URL : https://alta-shop.herokuapp.com/api/products/012/ratings 3. Klik tombol send | 404 not found | 200 Ok akan muncul rating yang dituju | PASSED
Product Create a comment for product | Create a comment for product with valid comment | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/products/108/comments 3. Input comment : "the games are great including Gran Turismo 7 but sadly GT4 is much better" 4. Klik tombol send | 200 Ok Akan membuat comment | 401 unauthorized | PASSED
| Create a comment for product with invalid comment | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/products/00/comments 3. Input comment : "" 4. Klik tombol send | 401 unauthorized | 401 unauthorized | PASSED
Product Get product comment | Get product comment with url | 1. Menyiapkan URL | 1. Method GET 2. URL : https://alta-shop.herokuapp.com/api/products/109/Comment 3. Klik tombol send | 200 Ok Akan muncul comment | 404 Not Found | PASSED
Product Categories Create a category | Create A Category with valid name and description | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/categories 3. Input name : "gaming" 4. Input description : "for gaming purposes" 5. Klik tombol send | 200 Ok Akan membuat category | 200 Ok Akan membuat category | PASSED
| Create A Category with null name | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/categories 3. Input name : "" 4. Klik tombol send | 500 Akan muncul error message | 500 Akan muncul error message | PASSED
| Create A Category with null name and null description | 1. Menyiapkan URL 2. Menyiapkan input body | 1. Method POST 2. URL : https://alta-shop.herokuapp.com/api/categories 3. Input name : "" 4. Input description : "" 5. Klik tombol send | 500 Akan muncul error message | 500 Akan muncul error message | PASSED